## Invoice (hidden)
INVOICE
Progress Claim # 23
To: | Region of Waterloo |  | Invoice Date: |  | 2017-07-31
| 150 Frederick Street, Kitchener, ON, N2G 4J3 |  | Invoice No.: |  | 23339
| 0 |  | Project: |  | Kitchener WWTP Contract 4 Tert Bldg & Outfall
| 0 |  | Maple Project Ref.: |  | 27-5003
Att: | Moorthy Darmalingum |  | HST Reg. No.: |  | 10349 0959 RT0003
| Senior Project Manager |  | Remit to: | 2026-08-05 | Maple Ball JV
2660 Argentia Road
Mississauga, ON
L5N 5V4
|  | Work to Date | Previously |  | Current Period
| Completed per Certificate: | 21431077.08 | 20478001.08 |  | 953076
| Holdback: | 2143107.708 | 2047800.108 |  | 95307.6
|  | 19287969.372 | 18430200.972 |  | 857768.4
| HST: | 2507436.0184 | 2395926.1264 |  | 111509.892
| Totals: | 21795405.3904 | 20826127.0984 |  | 969278.292
| Total due this invoice: |  | 969278.292
Maple Reinders Constructors Ltd. | [6 empty] | Constructors and Project Managers
2660 Argentia Road, Mississauga, ON L5N 5V4 |  |  |  |  | Tel: 905-821-4844 Fax: 905-821-4822
Click here to Print Invoice
Click here to Update last month's invoiced values

## PC# 24 (hidden)
|  |  | 0 |  |  | 0 | 0
|  |  | 0 |  |  | 0 | 0
|  |  | 0 |  |  | 0 | 0
[10 empty] | Add or delete rows: |  |  |  | Create a subsequent Certificate
Step 1:
Step 2:
Payment Certificate # 24
Kitchener WWTP Contract 4 Tert Bldg & Outfall
0%
2017-08-30
Item | Description | Breakdown Value | Completed to date | % to Date | Previous Claims | This Period | Balance to Complete | Deferred Value
| DIVISION 1 GENERAL |  | 0 |  | 0 | 0 | 0
1000 | General Requirements | 15000 | 14400 | 96% | 13800 | 600 | 600 | 600
01001A | Mobilization / Demobilization | 250000 | 220000 | 88% | 200000 | 20000 | 30000 | 30000
01001B | Bonds | 350000 | 350000 | 100% | 350000 | 0 | 0 | 0
01001C | Insurance | 175000 | 175000 | 100% | 175000 | 0 | 0 | 0
1100 | Summary of Work | 10000 | 10000 | 100% | 9200 | 800 | 0 | 0
1130 | Work Sequences and Tie-Ins | 2500 | 2500 | 100% | 2500 | 0 | 0 | 0
1135 | Co-ordination | 877508.12 | 857325.43 | 97.7% | 807307.47 | 50017.96 | 20182.69 | 20182.69 |  |  | 2.2792e-05
1140 | Work Restrictions | N/A | 0 |  | 0 | 0 | 0 | 0
1150 | Project Meeting | 15000 | 14400 | 96% | 13800 | 600 | 600 | 600
1200 | Alternatives | N/A | 0 |  | 0 | 0 | 0 | 0
1210 | Allowances | N/A | 0 |  | 0 | 0 | 0 | 0
1290 | Measurement and Payment | Incl Sect 01135 | 0 |  | 0 | 0 | 0 | 0
1320 | Project Schedules and Progress Reports | 65000 | 62400 | 96% | 59800 | 2600 | 2600 | 2600
1330 | Submittals (Record Drawings) | 500000 | 450000 | 90% | 230000 | 220000 | 50000 | 50000
1330 | Submittals (Balance of work excluding Record Drawings) | 3500 | 3500 | 100% | 1610 | 1890 | 0 | 0
1340 | Operating and Maintenance Data | 500000 | 250000 | 50% | 245000 | 5000 | 250000 | 250000
1355 | Project Waste Management | 12000 | 11520 | 96% | 11040 | 480 | 480 | 480
1400 | Environmental Protection | 5000 | 4800 | 96% | 4600 | 200 | 200 | 200
1410 | Regulatory Requirements | Incl Sect 01135 | 0 |  | 0 | 0 | 0 | 0
1420 | Reference Standards | Incl Sect 01135 | 0 |  | 0 | 0 | 0 | 0
1410 | Quality Control | 20000 | 19200 | 96% | 18400 | 800 | 800 | 800
1510 | Temporary Facilities | 25000 | 24000 | 96% | 23000 | 1000 | 1000 | 1000
1515 | Temporary Utilities | 12000 | 11520 | 96% | 11040 | 480 | 480 | 480
1565 | Project ID and Signs | 1500 | 1440 | 96% | 1380 | 60 | 60 | 60
1590 | Field Offices and Sheds | 36702 | 35233.92 | 96% | 33765.84 | 1468.08 | 1468.08 | 1468.08
1610 | Common Product Requirements | Incl Sect 01135 | 0 |  | 0 | 0 | 0 | 0
1720 | Field Engineering | 5000 | 4800 | 96% | 4600 | 200 | 200 | 200
1740 | Cleaning | 5000 | 3000 | 60% | 3000 | 0 | 2000 | 2000
1760 | Warranty Work | 10000 | 9600 | 96% | 9200 | 400 | 400 | 400
1770 | Closeout Procedures | 10000 | 9600 | 96% | 9200 | 400 | 400 | 400
1780 | Closeout Submittals | 8500 | 8160 | 96% | 7820 | 340 | 340 | 340
1785 | Spare Parts | Appl in Div11,15,16 | 0 |  | 0 | 0 | 0 | 0
1810 | Commissioning | 147000 | 147000 | 100% | 133770 | 13230 | 0 | 0 |  |  | 64310.77 | Div 1 outstanding, excluding O&M and asbuilts
1820 | Demonstration & Training | 5000 | 2500 | 50% | 2500 | 0 | 2500 | 2500 |  |  | 364310.77 | Div 1 outstanding, including O&M and asbuilts
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 2 SITE CONSTRUCTION |  | 0 |  | 0 | 0 | 0
2050 | Demolition | 75000 | 75000 | 100% | 75000 | 0 | 0
2137 | Bracing and Shoring | 650000 | 650000 | 100% | 650000 | 0 | 0
2140 | Dewatering | 210000 | 210000 | 100% | 210000 | 0 | 0
2200 | Earthwork and Structures | 330000 | 330000 | 100% | 326700 | 3300 | 0
2231 | Clearing and Grubbing | 75000 | 75000 | 100% | 75000 | 0 | 0
2232 | Tree Prunning | 5000 | 5000 | 100% | 0 | 5000 | 0
2233 | Preservation of Topsoil | 10000 | 10000 | 100% | 10000 | 0 | 0
2300 | Earthwork And Related Work | 140000 | 140000 | 100% | 138600 | 1400 | 0
2311 | Site Grading | 25000 | 22500 | 90% | 15000 | 7500 | 2500
2315 | Excavation, Trenching and Backfilling | 330000 | 330000 | 100% | 330000 | 0 | 0
2317 | Roadway Excavation, Embankment and Compaction | 180000 | 180000 | 100% | 180000 | 0 | 0
2355 | Caissons | 72500 | 72500 | 100% | 72500 | 0 | 0
2362 | Dust Control | 10000 | 10000 | 100% | 9200 | 800 | 0
2379 | Preservation of Watercourses | 10000 | 10000 | 100% | 10000 | 0 | 0
2380 | Erosion and Sedimentation Control | 45000 | 43200 | 96% | 37800 | 5400 | 1800
2390 | Soil Anchors | 250000 | 250000 | 100% | 250000 | 0 | 0
2431 | Mussel Relocation | 200000 | 186000 | 93% | 186000 | 0 | 14000 | 7000
2480 | Marine Work | 165000 | 165000 | 100% | 165000 | 0 | 0
2490 | Terrestrial Wildlife Protection | 10000 | 10000 | 100% | 9200 | 800 | 0
2511 | Watermains | 20000 | 20000 | 100% | 20000 | 0 | 0
2530 | Sewerage | 50000 | 50000 | 100% | 50000 | 0 | 0
2540 | Yard Piping | 4775000 | 4734890 | 99.16% | 4734890 | 0 | 40110 | 40110 | Delayed by C3
2555 | Telethermics | Incl in 02540 | 0 |  | 0 | 0 | 0
2581 | Duct Banks and Manholes | 12000 | 12000 | 100% | 12000 | 0 | 0
2631 | Chamber, Manholes and Catchbasins | 16000 | 16000 | 100% | 16000 | 0 | 0
2632 | Effluent Outfall CPP | 1180000 | 1180000 | 100% | 1180000 | 0 | 0
2641 | Pipe Culverts | 10000 | 10000 | 100% | 5000 | 5000 | 0
2701 | Aggregates | 10000 | 10000 | 100% | 9000 | 1000 | 0
2721 | Granular Base | 28300 | 26885 | 95% | 24055 | 2830 | 1415 | 1415
2723 | Granular Sub-base | 28300 | 27451 | 97% | 27451 | 0 | 849 | 849
2741 | Asphalt Paving | 59100 | 50235 | 85% | 0 | 50235 | 8865 | 8865
2752 | Concrete Curbs aand Paving | 18000 | 18000 | 100% | 0 | 18000 | 0
2800 | Planting | 20000 | 18000 | 90% | 0 | 18000 | 2000
2801 | Rehabilitation | 178980 | 170031 | 95% | 17898 | 152133 | 8949
2821 | Chain-Link Fence and Gate | 25000 | 24000 | 96% | 0 | 24000 | 1000
2822 | Ornamental Metal Fencing | 10000 | 2000 | 20% | 0 | 2000 | 8000
2911 | Topsoil and Finish Grading | 20000 | 16000 | 80% | 0 | 16000 | 4000
2933 | Sodding | 15000 | 13800 | 92% | 0 | 13800 | 1200
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 3 CONCRETE |  | 0 |  | 0 | 0 | 0
3100 | Concrete Forms and Accessories | 1720000 | 1720000 | 100% | 1720000 | 0 | 0
3200 | Concrete Reinforcement | 469700 | 469700 | 100% | 469700 | 0 | 0
3252 | Waterstops | 15000 | 15000 | 100% | 15000 | 0 | 0
3300 | Cast-in-Place Concrete | 405790 | 405790 | 100% | 405790 | 0 | 0
3361 | Concrete Floor Hardeners | 5000 | 5000 | 100% | 2500 | 2500 | 0
3400 | Precast Concrete | 76850 | 73007.5 | 95% | 69165 | 3842.5 | 3842.5 |  |  |  | Wall precast panels final touch-up and caulking
3410 | Structural Precast Prestressed Concrete | 300000 | 300000 | 100% | 300000 | 0 | 0
3610 | Equipment Grout | 8000 | 8000 | 100% | 8000 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 4 MASONARY |  | 0 |  | 0 | 0 | 0
4050 | Masonry Procedures | Incl in Sect 04211 | 0 |  | 0 | 0 | 0
4051 | Masonry Mortar and Grout | Incl in Sect 04211 | 0 |  | 0 | 0 | 0
4052 | Masonry Anchorage and Reinforcing | Incl in Sect 04211 | 0 |  | 0 | 0 | 0
4053 | Masonry Accessories | Incl in Sect 04211 | 0 |  | 0 | 0 | 0
4211 | Brick Masonry | 303100 | 300069 | 99% | 300069 | 0 | 3031
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 5 METALS |  | 0 |  | 0 | 0 | 0
5100 | Structural Steel | 216000 | 216000 | 100% | 216000 | 0 | 0
5311 | Steel Deck | 60000 | 60000 | 100% | 60000 | 0 | 0
5501 | Metal Fabrication - Architectural | 30000 | 30000 | 100% | 30000 | 0 | 0
5502 | Metal Fabrication - General | 42000 | 42000 | 100% | 42000 | 0 | 0
5503 | Metal Fabrication - Mechanical | 157000 | 157000 | 100% | 157000 | 0 | 0
5512 | Aluminum Handrails and Guards | 65000 | 61392.5 | 94.45% | 61392.5 | 0 | 3607.5 | 3607.5 | CO recently approved
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 6 WOOD |  | 0 |  | 0 | 0 | 0
06100 | Rough Carpentry | 47500 | 47500 | 100% | 47500 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 7 THERMAL & MOISTURE PROTECTION |  | 0 |  | 0 | 0 | 0
7100 | Waterproofing and Dampproofing | 236430 | 236430 | 100% | 235247.85 | 1182.15 | 0
7211 | Board Insulation | 10000 | 10000 | 100% | 10000 | 0 | 0
7219 | Sprayed Applied Insulation Polyurethane Foam | 3200 | 3200 | 100% | 3200 | 0 | 0
7270 | Air Barriers | 15000 | 15000 | 100% | 15000 | 0 | 0
7424 | Composite Metal Building Panels | 132760 | 132760 | 100% | 132760 | 0 | 0
7520 | SBS Modified Bituminous Membrane Roofing | 190300 | 190300 | 100% | 180309.25 | 9990.75 | 0
7620 | Sheet Metal Flashing and Trim | 15000 | 11000 | 73.33% | 15000 | -4000 | 4000 |  |  |  | Scuppers
7760 | Roof Pavers | Incl in Sect 07520 | 0 |  | 0 | 0 | 0
7840 | Fire Stopping | 20000 | 16000 | 80% | 16000 | 0 | 4000 |  |  |  | Provide a letter from the manufacturer indicating the closer angle is good enough and a test data to back it up, than verify with the building inspector that the fire stop material is not required.
7920 | Joint Sealants | 10500 | 5250 | 50% | 5250 | 0 | 5250
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 8 DOORS & WINDOWS |  | 0 |  | 0 | 0 | 0
8110 | Metal Doors and Frames | 92500 | 92500 | 100% | 74000 | 18500 | 0
8310 | Access Hatches | 2000 | 2000 | 100% | 2000 | 0 | 0
8330 | Overhead Coiling Doors and Grilles | 14970 | 14970 | 100% | 13473 | 1497 | 0
8400 | Aluminum Entrances | Incl in Sect 08110 | 0 |  | 0 | 0 | 0
8440 | Glazed Aluminum Curtain Walls | 82000 | 82000 | 100% | 77030.8 | 4969.2 | 0
8710 | Door Hardware | 15400 | 15400 | 100% | 13090 | 2310 | 0
8800 | Glazing | 50000 | 48800 | 97.6% | 48800 | 0 | 1200 |  |  |  | Corners and cleaning
8900 | Louvres and Vents | 1450 | 1450 | 100% | 0 | 1450 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 9 FINISHES |  | 0 |  | 0 | 0 | 0
9250 | Gypsum Board |  | 0 |  | 0 | 0 | 0
9900 | Painting | 18300 | 18300 | 100% | 16470 | 1830 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 10 SPECIALTIES |  | 0 |  | 0 | 0 | 0
10200 | Metal Louvres |  | 0 |  | 0 | 0 | 0
10400 | Signage | 2050 | 2050 | 100% | 2050 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 11 EQUIPMENT |  | 0 |  | 0 | 0 | 0
11010 | Equipment General Requirements | 17800 | 17800 | 100% | 17800 | 0 | 0
11090 | Identification of Equipment, Piping and Valves | 6630 | 3315 | 50% | 3315 | 0 | 3315
11100 | Miscellaneous Piping and Accessories Installation | Incl In Sect 11116 | 0 |  | 0 | 0 | 0
11110 | Ductile Iron Pipe | 6610 | 6610 | 100% | 6610 | 0 | 0
11116 | Piping, Valves and Fittings | 110000 | 110000 | 100% | 107800 | 2200 | 0
11170 | Pipeline Pressure and Leakage Testing | 4760 | 4760 | 100% | 4760 | 0 | 0
11190 | Pipe Supports | 12120 | 12120 | 100% | 12120 | 0 | 0
11280 | Fabricated Stainless Steel Sluice Gate | 362000 | 362000 | 100% | 362000 | 0 | 0
11283 | Fabricated Stainless Steel Stop Gates | 50000 | 50000 | 100% | 50000 | 0 | 0
11290 | Valve and Gate Actuators | 25000 | 25000 | 100% | 25000 | 0 | 0
11420 | Submersible Pumps | 25000 | 25000 | 100% | 25000 | 0 | 0
11751 | Installation of Tertiary Disk Filters | 95000 | 95000 | 100% | 95000 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 13 SPECIAL CONSTRUCTION |  | 0 |  | 0 | 0 | 0
13100 | C4 Instrumentation and Controls | 100000 | 100000 | 100% | 100000 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 14 CONVEYING SYSTEMS |  | 0 |  | 0 | 0 | 0
14630 | Travelling Bridge Crane | 15000 | 13500 | 90% | 12000 | 1500 | 1500
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 15 MECHANICAL |  | 0 |  | 0 | 0 | 0
15050 | Basic Mechanical Materials Requirements |  | 0 |  | 0 | 0 | 0
15070 | Vibration Isolation and Seismic Control | 2500 | 1250 | 50% | 1250 | 0 | 1250
15075 | Equipment, Piping and Valve Identification | 4000 | 1000 | 25% | 1000 | 0 | 3000
15080 | Piping Insulation | 27160 | 27160 | 100% | 13580 | 13580 | 0
15085 | Mechanical Insulation | Incl in Sect 15080 | 0 |  | 0 | 0 | 0
15184 | Refrigerant Piping | 4000 | 4000 | 100% | 4000 | 0 | 0
15191 | Fuel Gas Piping System | 12000 | 12000 | 100% | 12000 | 0 | 0
15305 | Portable Fire Extinguishers | 1000 | 1000 | 100% | 250 | 750 | 0
15412 | Domestic Water Supply Piping | 20000 | 20000 | 100% | 20000 | 0 | 0
15413 | Drainage, Waste and Vent Piping | 20000 | 20000 | 100% | 20000 | 0 | 0
15430 | Plumbing Specialties and Accessories | 25000 | 25000 | 100% | 25000 | 0 | 0
15440 | Plumbing Fixture and Trim | Incl in Sect 15440 | 0 |  | 0 | 0 | 0
15450 | Plumbing Equipment | 30000 | 30000 | 100% | 30000 | 0 | 0
15720 | Custom Made Air Handling Units | 180000 | 180000 | 100% | 180000 | 0 | 0
15770 | Air Conditioning Equipment | 20000 | 20000 | 100% | 20000 | 0 | 0
15810 | Ductwork and Accessories | 60000 | 60000 | 100% | 57000 | 3000 | 0
15815 | Gas Fired Equipment | 12000 | 12000 | 100% | 12000 | 0 | 0
15830 | Fans and Accessories | 30000 | 30000 | 100% | 30000 | 0 | 0
15900 | Automatic Controls | 95000 | 95000 | 100% | 80750 | 14250 | 0
15960 | HVAC Commissioning | 20000 | 10000 | 50% | 10000 | 0 | 10000 | 10000 | Natural gas not available (by C3)
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 16 ELECTRICAL |  | 0 |  | 0 | 0 | 0
16010 | Electrical General Requirements | 30000 | 30000 | 100% | 30000 | 0 | 0
16015 | Electrical System Analysis | 16000 | 16000 | 100% | 16000 | 0 | 0
16020 | Sequence of Activities | inc | 0 |  | 0 | 0 | 0
16051 | Installation of Cables in Trenches and Ducts | 90000 | 90000 | 100% | 90000 | 0 | 0
16090 | Equipment Identification | 2500 | 2500 | 100% | 1250 | 1250 | 0
16111 | Cable Tray Systems | 1800 | 1800 | 100% | 1800 | 0 | 0
16122 | Wires and Cables 0-1000V | 70000 | 70000 | 100% | 70000 | 0 | 0
16124 | Power Cable 1001-15000V | 145000 | 145000 | 100% | 145000 | 0 | 0
16131 | Splitters, Junction, Pull Boxes & Cabinets | 3500 | 3500 | 100% | 3500 | 0 | 0
16132 | Outlet Boxes, Conduit Boxes and Fittings | 1500 | 1500 | 100% | 1500 | 0 | 0
16133 | Conduits, Conduit Fastenings and Conduit Fittings | 91100 | 91100 | 100% | 91100 | 0 | 0
16141 | Wiring Devices | 14000 | 14000 | 100% | 14000 | 0 | 0
16199 | Electrical Inspection & Testing | 3500 | 3500 | 100% | 3500 | 0 | 0
16222 | AC Induction Motors | 0 | 0 |  | 0 | 0 | 0
16223 | Motor Starters to 600V | 0 | 0 |  | 0 | 0 | 0
16224 | Variable Frequency Drives to 600V | 0 | 0 |  | 0 | 0 | 0
16225 | Motor Control Centre | 125000 | 125000 | 100% | 125000 | 0 | 0
16271 | Dry Type Transformers | 2600 | 2600 | 100% | 2600 | 0 | 0
16400 | Basic Electrical Equip & Materials | 2500 | 2500 | 100% | 2500 | 0 | 0
16412 | Molded Case Circuit Breakers | 40000 | 40000 | 100% | 40000 | 0 | 0
16414 | Disconnect Switches-Fused & Unfused | 9000 | 9000 | 100% | 9000 | 0 | 0
16426 | Low Voltage Draw Out Metal Switchgear | 300000 | 300000 | 100% | 300000 | 0 | 0
16441 | Panelboards & Breaker Type | 4500 | 4500 | 100% | 4500 | 0 | 0
16450 | Grounding | 3900 | 3900 | 100% | 3900 | 0 | 0
16466 | Cable Bus-Low Voltage | 47000 | 47000 | 100% | 47000 | 0 | 0
16505 | Lighting Equipment | 65000 | 65000 | 100% | 65000 | 0 | 0
16531 | Exit Signs | 500 | 500 | 100% | 500 | 0 | 0
16536 | Emergency Lighting Units | 22000 | 22000 | 100% | 22000 | 0 | 0
16600 | Power Transformers | 140000 | 140000 | 100% | 140000 | 0 | 0
16671 | Surge Protective Devices | 0 | 0 |  | 0 | 0 | 0
16822 | Electric Heaters | 3500 | 3500 | 100% | 3500 | 0 | 0
16912 | Security Systems | 46600 | 9320 | 20% | 9320 | 0 | 37280 | 37280 | Direction from Region provided recently
|  |  | 0 |  | 0 | 0 | 0
| DIVISION 17 STRUCTURED CABLING & ENCLOSURES |  | 0 |  | 0 | 0 | 0
17100 | Structured Cabling and Enclosures | 57000 | 57000 | 100% | 57000 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
| PRE SELECTED EQUIPMENT |  | 0 |  | 0 | 0 | 0
2A | Supply of Tertiary Disk Filters (P2014-26) CO#2&3 Incl'd | 3291402 | 3291402 | 100% | 2633121.6 | 658280.4 | 0
2B | SCADA Integrator (P2013-01) | 61440 | 37294.08 | 60.7% | 37294.08 | 0 | 24145.92 | 24145.92 | IOs to be reconciled, outstanding balance is a credit not outstanding work
|  |  | 0 |  | 0 | 0 | 0
| PROVISIONAL ITEMS |  | 0 |  | 0 | 0 | 0
3.1 | Excavation in all kinds of soil, including removal of surplus materials |  | 0 |  | 0 | 0 | 0
| Up to 2.0 m deep | 7500 | 0 |  | 0 | 0 | 7500
| Up to 4.0 m deep | 4000 | 0 |  | 0 | 0 | 4000
| Up to 6.0 m deep | 7000 | 0 |  | 0 | 0 | 7000
3.2 | Soil Anchors (13 m long each) | 18000 | 0 |  | 0 | 0 | 18000
3.3 | Concrete caisons (1200mm Ø), including drilling, concrete, rebar, and casing |  | 0 |  | 0 | 0 | 0
| 1. Addition: increase caisson length by more than 0.5 m | 9600 | 0 |  | 0 | 0 | 9600
| 2. Deduction: decrease caisson length by more than 0.5 m | Rate Only | 0 |  | 0 | 0 | 0
| 3. Addition: Added caisson | 16000 | 0 |  | 0 | 0 | 16000
| 4. Deduction: Deleted piles | Rate Only | 0 |  | 0 | 0 | 0
3.4 | Cast-in-place concrete as specified including formwork and finishing but excluding reinforcing steel |  | 0 |  | 0 | 0 | 0
| 30 MPa Concrete Slabs on Grade & Equipment Bases | 9750 | 0 |  | 0 | 0 | 9750
| Reinforcing Steel | 6000 | 0 |  | 0 | 0 | 6000
| Concrete Fill (unreinforced 20Mpa) | 2500 | 0 |  | 0 | 0 | 2500
3.6 | Structural Steel | 9000 | 0 |  | 0 | 0 | 9000
3.7 | Removal and disposal of unsuitable material from project site (non-contaminated) | 100000 | 0 |  | 0 | 0 | 100000
3.8 | Removal and disposal of contaminated material from project site | 200000 | 0 |  | 0 | 0 | 200000 |  |  |  | 389350
|  |  | 0 |  | 0 | 0 | 0
| CONTINGENCY ALLOWANCE |  | 0 |  | 0 | 0 | 0
| Contingency Allowance | 1885229.75 | 0 |  | 0 | 0 | 1885229.75
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
Total |  | 25525191.87 | 22686191.43 | 88.88% | 21299545.39 | 1386646.04 | 2839000.44
Change Orders:
CO-001 | Decommission Boreholes | 958 | 958 | 100% | 958 | 0 | 0
CO-002 | Disk Filter Alternate Bid | -336912 | -336912 | 100% | -269529.6 | -67382.4 | 0
CO-003 | Credit for Filter Covers | -2402.18 | -2402.18 | 100% | -1921.74 | -480.44 | 0
CO-004 | Erosion Control Mats and Silt Fence | 49314 | 49314 | 100% | 41541.13 | 7772.87 | 0
CO-005 | Supply MHCC Stop Gate | 12002 | 12002 | 100% | 12002 | 0 | 0
CO-006 | Equipment Estimates Consultant Trailer | 7386 | 7386 | 100% | 6204.24 | 1181.76 | 0
CO-007 | FO-001 Utility Disconnection | 16466 | 16466 | 100% | 16466 | 0 | 0
CO-008 | FO-002 Deep Observation Well | 15523 | 15523 | 100% | 15523 | 0 | 0
CO-009 | FO-003 Chemical Cleanout | 1460 | 1460 | 100% | 1460 | 0 | 0
CO-010 | RFQ-006 Effluent Pump VFD's | 56362 | 56362 | 100% | 56362 | 0 | 0
CO-011 | RFQ-007 Precast Panel Vert Reveals | 2470 | 2470 | 100% | 2470 | 0 | 0
CO-012 | RFQ-009 Brick Change to Match Ex'g | 59581.38 | 59581.38 | 100% | 58985.57 | 595.81 | 0
CO-013 | RFQ-008 Level Sensor in Chamber C-C | 11719.44 | 11719.44 | 100% | 10547.5 | 1171.94 | 0
CO-014 | Utility Usage Until Nov 23 2016 | -14494.65 | -14494.65 | 100% | -14494.65 | 0 | 0
CO-015 | RFQ-010 Effluent Outfall Access Chamber Mods | 23277.2 | 23277.2 | 100% | 23277.2 | 0 | 0
CO-016 | CR-005 Buried Conditions of 3000 CPP | 2342.58 | 2342.58 | 100% | 2342.58 | 0 | 0
CO-017 | CR-007 Mods on Solids Wasting Pipe | 2988.5 | 2988.5 | 100% | 2988.5 | 0 | 0
CO-018 | CR-008 Effluent Pump VFD Mods | 7691.4 | 7691.4 | 100% | 7691.4 | 0 | 0
CO-019 | FO-004 Black PVC Pipe Removal | 7192 | 7192 | 100% | 7192 | 0 | 0
CO-020 | FO-005 Trail Closure Signs | 3140 | 3140 | 100% | 3140 | 0 | 0
CO-021 | FO-006 Gate Recess Add'l Rebar | 1187 | 1187 | 100% | 1187 | 0 | 0
CO-022 | CR-18 Conduits in EC Basement | 14047 | 14047 | 100% | 14047 | 0 | 0
CO-023 | CR-015 Increase size of Eff Waterlines | 3541.2 | 3541.2 | 100% | 3541.2 | 0 | 0
CO-024 | CR-003 Change Outfall Bedding Mat'l | 4293 | 4293 | 100% | 4293 | 0 | 0
CO-025 | CR-006 Damaged Cable Chamber GG | 9641 | 9641 | 100% | 9641 | 0 | 0
CO-026 | CR-014 Delete Concentric Neutral | -10000 | -10000 | 100% | -10000 | 0 | 0
CO-027 | RFQ-12 Fall Restraint Anchors | 4877 | 4877 | 100% | 4877 | 0 | 0
CO-028 | CR-017 Chamber GG Size Increase | 5335 | 5335 | 100% | 5335 | 0 | 0
CO-029 | CR-026 ReMount HMI Bezels Filter VFD | 6350 | 6350 | 100% | 6350 | 0 | 0
CO-030 | CR-019 Mud Mats Under Outfall | 4330.64 | 4330.64 | 100% | 4330.64 | 0 | 0
CO-031 | CR-27 Install Add'l 30A Bucket MCC17 | 4765 | 4765 | 100% | 4765 | 0 | 0
CO-032 | CR-20 Additional Beam at Xfrmr | 5902 | 5902 | 100% | 5902 | 0 | 0
CO-033 | CR-04 Drill Rig New Regulations | 17649.23 | 17649.23 | 100% | 17649.23 | 0 | 0
CO-034 | CR-23 Additional Ductbank | 7322.89 | 7322.89 | 100% | 7322.89 | 0 | 0
CO-035 | CR-10-R1 Watermain at East Stair | 3394.08 | 3394.08 | 100% | 3394.08 | 0 | 0
CO-036 | CR-11 Additional Concrete Topping | 2180.3 | 2180.3 | 100% | 2180.3 | 0 | 0
CO-037 | CR-39 Install Pest Control Lights | 11448.57 | 11448.57 | 100% | 11448.57 | 0 | 0
CO-038 | RFQ-041 Temporary Backwash Piping | 12810.85 | 12810.85 | 100% | 12810.85 | 0 | 0
CO-039 | LAD-SAF Ladder Safety System | 3084.82 | 3084.82 | 100% | 0 | 3084.82 | 0
CO-040 | RFQ-020 Digital Signal Wiring | 9676.5 | 9676.5 | 100% | 9676.5 | 0 | 0
CO-041 | CR-28 Potable Water Meter | 4712.5 | 4712.5 | 100% | 4712.5 | 0 | 0
CO-042 | CR-33 RFQ-11 Partial Release | 62157 | 24862.8 | 40% | 24862.8 | 0 | 37294.2 | 37294.2
CO-043 | CR-33a RFQ-011-R1 Equipment | 185005 | 0 | 0% | 0 | 0 | 185005 | 185005 | Additional work, CO recently issued
CO-044 | CR-35 RFI-124-0 Potable PRV | 4624.75 | 4624.75 | 100% | 0 | 4624.75 | 0
CO-045 | FO-007 Watermain Modifications | 6454 | 6454 | 100% | 0 | 6454 | 0
CO-046 | CR-009 IO Level Sensor Chamber CC | 3394 | 0 | 0% | 0 | 0 | 3394 | 3394 | Additional work, CO recently issued
CO-047 | RFQ-016 Delete Call Out Wiring | -3600 | -3600 | 100% | 0 | -3600 | 0
CO-048 | CR-049 Curb Extra | 10199.6 | 10199.6 | 100% | 0 | 10199.6 | 0
|  |  | 0 |  | 0 | 0 | 0
Total Change Orders |  | 320847.6 | 95154.4 | 29.66% | 131531.69 | -36377.29 | 225693.2
Total Revised Contract |  | 25846039.47 | 22781345.83 | 88.14% | 21431077.08 | 1350268.75 | 3064693.64
723276.39
add one row to certificate
delete bottom row of certificate
add one row to change orders
Click here, if last months certificate was verified accepted
Click here, to Update Last Month's Progress as Previously Claimed

## SubstantialCalc (hidden)
Review of Substantial Performance Values
Total Original Contract Price |  |  | 25639962.12
Maximum Value of Uncompleted Work (Based on Original Contract Price)
| a) 3% of $500,000 |  | 15000
| b) 2% of $500,000 |  | 10000
| c) 1% or remainder |  | 246399.6212
|  | Total | 271399.6212
Deductions from Contract Amount
| Work Yet to Complete (Agreed as Excluded from Calculation) |  | 758276.39
| Remaining Contract Contingency (COs 1-49) |  | 1679152.4
| Remaining Provisional Items |  | 389350
|  | Total | 2826778.79
Contract Amount for Determining Substantial Performance |  |  | 22813183.33
Maximum Value of Uncompleted Work (Based on Contract Amount for Determining Substantial Performance)
| a) 3% of $500,000 |  | 15000
| b) 2% of $500,000 |  | 10000
| c) 1% or remainder |  | 218131.8333
|  | Total | 243131.8333
Cost Completion to Date (Confirmed in Site Review on August 31, 2017) |  |  | 22572470.83
Does Contract meet Substanial Completion Financial Requirement? |  |  | YES, IT DOES MEET
Amount to complete to meet Substantial Performance (if negative exceeds requirement) |  |  | -2419.3333

## Deficiencies (hidden)
|  |  | Project: | KWWTP Contract 4 | Address: | 368 Mill Park Drive Kitchener, ON N2P 2B4 | Effective Date: | 2017-08-30
|  |  | Client: | RMOW | Contract No.: | T2015-129
|  |  | Client Rep: | David Brook | Contractor: | Maple Ball Joint Venture
Item # | Inc / Def | Division | Spec | Spec Section | Location | Description / Note | Recommended Resolution | Deferred | Deficiency | Balance to Complete | Status
1 | Incomplete | 1. General | 1000 | General Requirements
2 | Incomplete | 1. General | 01001A | Mobilization / Demobilization
3 | Incomplete | 1. General | 1100 | Summary of Work
4 | Incomplete | 1. General | 1135 | Co-ordination
5 | Incomplete | 1. General | 1150 | Project Meeting
6 | Incomplete | 1. General | 1320 | Project Schedules and Progress Reports
7 | Incomplete | 1. General | 1330 | Submittals (Record Drawings)
8 | Incomplete | 1. General | 1340 | Operating and Maintenance Data
9 | Incomplete | 1. General | 1355 | Project Waste Management
10 | Incomplete | 1. General | 1400 | Environmental Protection
11 | Incomplete | 1. General | 1410 | Quality Control
12 | Incomplete | 1. General | 1510 | Temporary Facilities
13 | Incomplete | 1. General | 1515 | Temporary Utilities
14 | Incomplete | 1. General | 1565 | Project ID and Signs
15 | Incomplete | 1. General | 1590 | Field Offices and Sheds
16 | Incomplete | 1. General | 1720 | Field Engineering
17 | Incomplete | 1. General | 1740 | Cleaning
18 | Incomplete | 1. General | 1760 | Warranty Work
19 | Incomplete | 1. General | 1770 | Closeout Procedures
20 | Incomplete | 1. General | 1780 | Closeout Submittals |  | Progress photos Test results and reports to be submitted via Aconex (testing and commissioning reports; test data for piping systems (degreasing, flushing, disinfection); hydrostatic or air tests performance, leakage/pressure testing, ...)
21 | Incomplete | 1. General | 1820 | Demonstration & Training
22 | Incomplete | 2. Site Construction | 2311 | Site Grading
23 | Incomplete | 2. Site Construction | 2380 | Erosion and Sedimentation Control
24 | Incomplete | 2. Site Construction | 2431 | Mussel Relocation
25 | Incomplete | 2. Site Construction | 2490 | Terrestrial Wildlife Protection
26 | Incomplete | 2. Site Construction | 2540 | Yard Piping
27 | Incomplete | 2. Site Construction | 2721 | Granular Base
28 | Incomplete | 2. Site Construction | 2723 | Granular Sub-base
29 | Incomplete | 2. Site Construction | 2741 | Asphalt Paving
30 | Incomplete | 2. Site Construction | 2800 | Planting
31 | Incomplete | 2. Site Construction | 2801 | Rehabilitation
32 | Incomplete | 2. Site Construction | 2821 | Chain-Link Fence and Gate
33 | Incomplete | 2. Site Construction | 2822 | Ornamental Metal Fencing
34 | Incomplete | 2. Site Construction | 2911 | Topsoil and Finish Grading
35 | Incomplete | 2. Site Construction | 2933 | Sodding
36 | Incomplete | 3. Concrete | 3400 | Precast Concrete |  | Precast wall panels to be cleaned of blue skin, mortar, etc and bottom brackets to be cut (sticking out), shims to be removed Damaged West wall precast to be repaired
37 | Incomplete | 4. Masonry | 4211 | Brick Masonry |  | Brick veneer to be cleaned, joints to be caulked, brick to be fixed West end (hit by a lift). On the north facade, west side is not properly installed (angled). Inadequate vent holes provided below first veneer shelf angle and weep holes at bottom of wall. 2 louvers to be completed Chipped corner of the landing to be patched in the West Stairwell | Provide additional insect screen accessories placed horizontally between the top of precast panel and underside of veneer shelf angle to maintain minimum vent hole spacing. Provide additional insect screen accessories placed horizontally at bottom of wall between the underside of precast panel and top of foundation ledge to maintain minimum vent hole spacing. Sealant to be installed around precast panel except at bug screen locations.
38 | Incomplete | 5. Metals | 5512 | Aluminum Handrails and Guards |  | The centre post needs to be removable at railing gate Roof door threshold plate is missing
39 | Incomplete | 7. Thermal&Moisture Prot. | 7520 | SBS Modified Bituminous Membrane Roofing |  | Splash pad for west stair tower scupper is missing
40 | Incomplete | 7. Thermal&Moisture Prot. | 7620 | Sheet Metal Flashing and Trim |  | 4 scuppers to be completed
41 | Incomplete | 7. Thermal&Moisture Prot. | 7840 | Fire Stopping
42 | Incomplete | 7. Thermal&Moisture Prot. | 7920 | Joint Sealants
43 | Incomplete | 8. Doors&Windows | 8110 | Metal Doors and Frames |  | Glazing to be completed
44 | Incomplete | 8. Doors&Windows | 8800 | Glazing |  | Glazing to be sealed at building corners; stickers to be removed and cleaned
45 | Incomplete | 8. Doors&Windows | 8900 | Louvres and Vents |  | Louvre on electrical room wall should have firestopping
46 | Incomplete | 11. Equipment | 11090 | Identification of Equipment, Piping and Valves
47 | Incomplete | 14. Conveying Systems | 14630 | Travelling Bridge Crane
48 | Incomplete | 15. Mechanical | 15070 | Vibration Isolation and Seismic Control
49 | Incomplete | 15. Mechanical | 15075 | Equipment, Piping and Valve Identification
50 | Incomplete | 15. Mechanical | 15960 | HVAC Commissioning
51 | Incomplete | 16. Electrical | 16912 | Security Systems
52 | Incomplete | Pre-Selected Eq. | 2B | SCADA Integrator (P2013-01)
53 | Incomplete | Change Orders | CO-004 | Erosion Control Mats and Silt Fence
54 | Incomplete | Change Orders | CO-006 | Equipment Estimates Consultant Trailer
55 | Incomplete | Change Orders | CO-012 | RFQ-009 Brick Change to Match Ex'g
56 | Incomplete | Change Orders | CO-013 | RFQ-008 Level Sensor in Chamber C-C
57 | Incomplete | Change Orders | CO-027 | RFQ-12 Fall Restraint Anchors
58 | Incomplete | Change Orders | CO-039 | LAD-SAF Ladder Safety System
59 | Incomplete | Change Orders | CO-042 | CR-33 RFQ-11 Partial Release
60 | Incomplete | Change Orders | CO-043 | CR-33a RFQ-011-R1 Equipment
61 | Incomplete | Change Orders | CO-046 | CR-009 IO Level Sensor Chamber CC
62 | Deficiency | 1. General |  |  | Several Locations | Catch Basins cleaning & damage at several locations | Vac inside, remove filter cloths |  | 2000
63 | Deficiency | 1. General | 1340 |  |  | Shop Drawingswith R&R status are to be resubmitted (see email on June 15, 2017) |  |  | 0 |  | Completed
64 | Deficiency | 2. Site Construction | 2752 |  | West of Blower Building | Damaged curb section at the corner in front of the blower building | Remove the damaged curb section and pour it again |  | 1000
65 | Deficiency | 2. Site Construction |  |  | West of TFB on both sides of the road East of TFB at chamber B & South of TFB under electrical platform | Ripraps to be completed, More gravel to be added around electrical platform up to asphalt |  |  | 2000
66 | Deficiency | 2. Site Construction |  |  | Fenced area under the electrical room and transformers platform | Switch this area from ‘topsoil and sod’ to ‘gravel’ as per FI-016 | Fence will not be connected to the building, need 2 posts next to building at both ends |  |  |  | CR approved
67 | Deficiency | 2. Site Construction | 2140 | Dewatering |  | Provide dewatering records (daily volume) for 2017 |  |  |  |  | Completed
68 | Deficiency | 2. Site Construction |  | Excess material removal |  | $20/m3 |  | 24000 |  |  | 20% left
69 | Deficiency | 3. Concrete |  |  | Throughout building Throughout building South Façade Electrical Room Throughout building Basement Basement | All wall and floor/ceiling penetrations for electrical & plumbing to be sealed All electrical penetrations for conduits to be sealed Effluent line penetration on flood wall to be sealed Hole on the ceiling to be patched All unnecessary screws to be removed and holes to be patched North (channel) wall tie holes need to be patched properly Sump pump - stair wall to be patched and cleaned | MBJV to submit a proposed solution for the openings |  |  |  | Double counted with 07920 and sack rub/painting
70 | Deficiency | 3. Concrete | 3300 | Cast-in-Place Concrete | West Stairwell East Stairwell | Leaking along the channel wall Leaking from the concrete joint | Polyurethane injection Polyurethane injection |  |  |  | Completed | Nothing done in the east stairwell but it is dry now. Needs to be monitored.
71 | Deficiency | 3. Concrete |  |  | Basement | Diagonal cracks at hatch corners on the ceiling | CIMA to review |  | 1000
72 | Deficiency | 3. Concrete |  |  | Ground Floor | Swing stage channel drains pipes to be cut and new 1/4" drain holes to be drilled as they are higher than the channel bottom & put skimcoat |  |  | 0 |  | Completed
73 | Deficiency | 3. Concrete | 3410 |  | Roof Double Tees | Clean double tees of mud&other marks, caulk joints of double tees |  |  | 3375 |  |  | Cleaning is completed
74 | Deficiency | 3. Concrete |  |  | Throughout building | Interior walls are to be sack-rubbed/painted |  |  | 75000
75 | Deficiency | 3. Concrete |  |  | All Façades & Columns, Stair wing walls | Concrete section above grade to be cleaned and uniform, holes under the electrical room to be patched | Clean, grind where needed, sack run exterior stair wing walls |  | 2000
76 | Deficiency | 3. Concrete |  |  | Throughout building | All concrete edges need to be cleaned & rounded including windows' horizontal & vertical edges. |  |  | 0 |  | Completed
77 | Deficiency | 3. Concrete |  |  |  | Chamber G-G has no reveals | MBJV to submit a proposal; Region suggest epoxy coating |  | 5000
78 | Deficiency | 4. Masonry | 4211 |  | South Façade South Façade Transformer platforms | Tar splattered by roofers on the South façade, columns, under the electrical room (4 sections), on flashings and stair tower wall on the roof Horizontal joint where the electrical room slab meets brick veneer to be sealed Missing bricks below panels Brick joints to be caulked (including the roof) | Vendor report to be submitted on sandblasted surface; to be replaced if surface has been damaged |  | 5000
79 | Deficiency | 5. Metals |  |  | Ground Floor | Gaps on filter chain and motor guards to be minimized | Filter chain guards have too large of a gap; need to minimize gaps to less than a finger width. |  | 2000
80 | Deficiency | 5. Metals |  |  | Ground Floor | Hatch handle boxes and checkered plates lifting corners need drain holes | 1/4" drain holes on each handle box and each lifting corners |  |  |  |  | Hide it as the water drained slowly
81 | Deficiency | 5. Metals | 5501 |  | Ground Floor | Handrails around filter tank |  |  |  |  | Double counted under 05512
82 | Deficiency | 7. Thermal&Moisture Prot. |  |  |  | Insulation and soffit to be completed underside the electrical room |  |  | 20000
83 | Deficiency | 7. Thermal&Moisture Prot. | 7520 |  | Electrical Room | Leaking from the hole on the double tees - where there are 2 cones on the roof Leaking on the east wall/ceiling - wheather station area |  |  | 3000
84 | Deficiency | 11. Equipment |  |  | Basement | Backwash pumps causing serious vibrations on the pipes | Vibration test reports needed |  | 2000 |  |  | Serious vibration witnessed on #2 on Sep 15, 2017
85 | Deficiency | 11. Equipment | 11090 |  |  | Provide chain wheel for valve operators located more than 2 m from finished floor (9) |  |  | 0
86 | Deficiency | 13. Special Construction | 13100 | I&C |  | See SAT document |  | 1000
87 | Deficiency | 13. Special Construction | 13100 | I&C |  | See SAT document |  | 1000
88 | Deficiency | 13. Special Construction | 13100 | I&C |  | See SAT document |  | 1000
89 | Deficiency | 13. Special Construction | 13100 | I&C |  | See SAT document |  | 1000
90 | Deficiency | 13. Special Construction | 13100 | I&C |  | See SAT document |  | 1000
91 | Deficiency | 15. Mechanical | 15810 |  | Roof | Roof duct support shop dwg submitted providing calculations for uplift and overturning of the supports | Roof duct supports feet are not permitted, needs 300mm x 300mm rubber support pads |  | 0
92 | Deficiency | 15. Mechanical |  |  | Basement | Potable water line to be sealed | Link-seal |  | 0 |  | Completed
93 | Deficiency | 16. Electrical |  |  | Ground Floor & Mezzanine | Flood lights need to be adjusted to illuminate each filter tank | To be verified with S-S |  | 0 |  | Completed
94 | Deficiency | 16. Electrical | 16505 |  | Throughout building | 2 broken light covers | To be checked and replaced |  | 500
95 | Deficiency | 16. Electrical |  |  |  | Electrical System Analysis' submissions |  |  | 0 |  | Completed
96 | Deficiency | 16. Electrical | 16010 |  |  | Installation of the arc flash labels on the switchgear, MCC and the PLC panels | The arc flash labels are to be installed in accordance with 16199. |  | 0
97 | Deficiency | Pre-Selected Eq. |  |  |  | 1. Filter 2 LSH1: On the filter overview screen, filter‎ 2 LSH1 is blinking as active, but on the filter 2 screen it is not 2. Setpoint screens allow setpoint changes when logged in as Guest 3. RPU05, 45, 46, 48 and 49 need to be added to the Logix clock update tool on SRV02. RPU05 is currently reading Feb 10, 1998, 5:00 AM. |  | 1000
98 | Deficiency | 4. Masonry | 4211 |  |  | Brick veneer to be cleaned and incomplete or missing joints to be repointed. Loose brick to be fixed & missing mortar to be completed, damage on the north wall |  |  | 2000
99 | Deficiency | 7. Thermal& Moisture Prot. | 7520 |  | Roof | Tar splattered by roofers to the claddings, flashings and West Stariwell walls, ladder to be cleaned | To be cleaned |  | 5000
100 | Deficiency | 11. Equipment | 11290 |  | In front of UVDF | Replace 2 damaged valve boxes with new valve box assembly |  |  |  |  | Completed
101 | Deficiency | 11. Equipment | 11290 |  | Outfall chamber | Cut valve box on top of the chamber to grade (see C-102-3). |  |  | 1500 |  |  | Brad to confirm
102 | Deficiency | 11. Equipment | 11420 |  |  | Sump pump davit crane and certificate |  |  | 7500
103 | Deficiency | 15. Mechanical | 15430 |  |  | Roof leaking from drain opening over filter checker plates |  |  | 2000
104 | Deficiency | 16. Electrical | 16090 |  |  | Conduit markers missing |  |  | 5000
105 | Deficiency | 16. Electrical | 16531 |  |  | Exit sign at the east stairwell seems still charging | Battery to be replaced if necessary |  | 0 |  | Completed
106 | Deficiency | Pre-Selected Eq. | 2A |  |  | 1. Filters are stuck in constant backwash mode and need reset. 2.Frequent nuisance Backwash pump pressure alarms. They pop up and clear quickly. |  | 5000
107 | Deficiency |  | 1720 |  |  | Topographical survey of the final works need to be submitted |  |  |  |  | Included in record drawings
108 | Deficiency |  |  |  |  | Scuppers are to be fixed |  |  |  |  | Double counted in 07620
109 | Deficiency |  |  |  |  | Door sweepers are missing at stairs |  |  | 0
110 | Deficiency |  |  |  |  | Electrical Room louver requires fire damper to meet code |  |  |  |  | Under fire stop
111 | Deficiency |  |  |  |  | CIMA to review occupany report and add items to list or issue RFQ(s) as required | City granted occupancy on Sep 14, 2017 |  |  |  | Completed
112 | [5 empty] | Work platform to be taken inside the building and tested in a filter tank | Coordinate with Kyle |  | 1000
113 |  |  |  |  | NW corner of TFB | Sidewalk crack is not acceptable | MBJV to submit a proposal |  | 2000
114 |  |  |  |  | East of TFB | Drainage swale to be extended on north of Chamber B |  |  |  |  | Completed
115 |  |  |  |  | East of TFB | Overhead door sensor to be adjusted |  |  | 500 |  |  | Reported completed, to be verified
116 |  |  |  |  | Electrical Room | Roof drain pipe collar to be fixed/replaced |  |  | 1000
117 |  |  |  |  | Weather Station | 3 issues to be resolved: humidity, rain gauge and wind speed |  |  | 1000
118 |  |  |  |  | Basement | Backwash valve leaking (on the 4th) |  |  |  |  | Completed
119 |  |  |  |  | East Stairwell | Window trims are missing on both sides External door sill missing |  |  | 1000
120 |  |  |  |  | Transformers | Installation of the arc flash and dual feed labels on the transformers | The arc flash labels are to be installed in accordance with 16199. |  | 500
121 |  |  |  |  | Roof | AHU door stopper to be provided, garbage inside AHU to be removed, touch-up paint to be done |  |  | 500
122 |  |  |  |  | Ground floor | Eye wash units foot pedals to be adjusted, hot water/tempered water/potable water and shower systems to be verified. |  |  | 1000
123 |  | 16. Electrical |  |  | Mezzanine | Open outlet - security
124 |  | 16. Electrical |  |  | Electrical Room | Power markers are missing, gaskets around circuit breakers to be placed properly |  |  | 500
125 |  |  |  |  | Loading Bay | Hose reel to be relocated to the right side of the effluent water line |  |  |  |  | OCWA request
126 |  | 7. Thermal& Moisture Prot. |  |  | Roof | West stairwell downspout splash pad is missing |  |  | 500
127 |  |  |  |  | Loading Bay | Spare parts to be placed against the wall |  |  |  |  | OCWA request
128 | [5 empty] | Scuppers flashing and roof membrane transitions to be installed properly |  |  |  |  | Included in incomplete work value
129 | [5 empty] | Damaged precast wall panels to be repaired, |  |  | 2500
130 |  |  |  |  | West Stairwell | Repair chipped landing in West Stairwell |  |  | 500
131 |  |  |  |  | West Stairwell | Provide roof door threshold plate |  |  | 500
132 |  |  |  |  | Roof | Provide splash pad for West Stair tower scupper |  |  | 500
133 | [5 empty] | All exterior curtain walls outside corners missing sealant |  |  | 500
134 |  |  |  |  | Transformers platform | Concrete curb missing in two locations at transformer slab to wall transition, refer to detail 2/A102-A |  |  | 5000
135 |  |  |  |  | Under transformers platform | Brick wrapped columns, supporting exterior transformer platform are missing caps, refer to detail 5/A502-A |  |  | 3000
136 | [5 empty] | Touch-up damaged paint on all doors and doorframes and equipment |  |  | 1000
137 |  |  |  |  | East wall | Electrical conduit and gas penetrations on the east wall to be sealed |  |  | 500
138 |  |  |  |  | East wall | OH door jambs to be caulked, to be touched-up with zinc-rich paint |  |  | 500
139 |  |  |  |  | Laoding Bay | Insulation of pipes at Loading Bay to be completed |  |  | 500
140 |  |  |  |  | Mezzanine | Mezzanine handrail gate latch to be replaced |  |  | 500
141 |  |  |  |  | Roof | AHU ductwork to be insulated and weather-stripped |  |  | 2000
142 |  |  |  |  | Civil | Road preparation and asphalt at connection piece |  |  |  |  | Included in incomplete work value
[7 empty] | TOTAL HOLDBACK | 35000 | 173875
[7 empty] | TOTAL BALANCE TO COMPLETE |  |  | 0
Asphalt at connection piece

## Defiency and Outstanding Work
Master Deficiency List
Project Name: | [5 empty] | Contractor:
Region Contract No.: | [5 empty] | Date: | [6 empty] | 2026-08-05
Item No. | Project Stage | Location | Description | Specification/ Drawing Reference | Holdback Value | Date Identified | REQUIRED FOR SUBSTANTIAL | CALENDAR DAYS TO CONFIRMED COMPLETION | DAYS OUTSTANDING FOR INCOMPLETE ITEMS | BALANCE TO COMPLETE | Required for Final Completion | Status | Comment | Target Completion Date | Confirmed Completion Date
|  |  | Total Holdback |  | 0

## Options
Project Stage | Status
Prior to Substantial | Open
Warranty Period | Closed